## Slide 1
AI Driven Fleet
Optimization
Implementation Plan to Phase 04 Completion
Backend foundation • MongoDB Atlas • Authentication • Core APIs • Predictive Maintenance ML integration
50%
target milestone
Web
React frontend
API
FastAPI backend
DB/ML
MongoDB + models
Prepared for supervisor presentation and Codex implementation sequencing

## Slide 2
Project status snapshot
Current implementation state and exact gap before Phase 01 starts
AI Driven Fleet Optimization
CURRENT STATE
Phase 01–04 implementation plan | Slide 2
Done
Web frontend
Done
Mobile frontend
Ready
ML artifacts
Missing
Real backend
Missing
Database
Missing
API wiring
What exists
React web UI, Flutter driver UI, three trained ML artifact ZIPs, and mock/demo service flows.
What is missing
Backend APIs, MongoDB Atlas persistence, authentication, real prediction endpoints, and service integration.
Phase 01–04 target
Convert the project from frontend prototype to backend-connected research prototype for predictive maintenance.
Estimated current project completion
35%
Target after Phase 04 completion
50%

## Slide 3
Target architecture by Phase 04
The backend becomes the integration layer between existing frontends, MongoDB, and ML artifacts
AI Driven Fleet Optimization
ARCHITECTURE
Phase 01–04 implementation plan | Slide 3
React Web App
Admin dashboard, vehicles, maintenance, predictions
Flutter Driver App
Driver login, route, alerts, issue report
FastAPI Backend
Auth, role middleware, vehicle APIs, maintenance APIs, prediction APIs, alert orchestration
MongoDB Atlas
Users, vehicles, parts, maintenance, predictions, alerts
EV PM Model Artifact
Failure probability, maintenance type, estimated RUL
Future Phase Artifacts
Route ETA/delay + demand forecasting models organized for next integration
Phase 04 boundary
At Phase 04, predictive maintenance becomes API-backed and persisted. Route + demand artifacts are organized but full model integration happens after the 50% milestone.

## Slide 4
ML artifact readiness
Three model artifacts exist, but only EV predictive maintenance is integrated by Phase 04
AI Driven Fleet Optimization
ARTIFACTS
Phase 01–04 implementation plan | Slide 4
Predictive Maintenance
Artifact: ev_pm_artifacts.zip
Core output: failure probability
Status by Phase 04: integrated into API
Key metric: failure F1 = 84.59%
Route Prediction
Artifact: route_prediction_artifacts.zip
Core output: ETA + delay risk
Status by Phase 04: organized only
Key metric: delay ROC-AUC = 97.03%
Demand Forecasting
Artifact: demand_forecasting_artifacts.zip
Core output: zone demand forecast
Status by Phase 04: organized only
Note: baseline currently stronger than graph-enhanced
Chart: 
| EV failure F1 | Route delay AUC | Demand baseline MAE* | Graph MAE*
Model quality / readiness | 84.59 | 97.03 | 4.35 | 6.53
*Demand MAE is an error metric; lower is better. This chart shows it on the same scale only for presentation comparison.

## Slide 5
Roadmap to first 50% completion
Phases 01–04 turn the project into a backend-connected prototype
AI Driven Fleet Optimization
ROADMAP
Phase 01–04 implementation plan | Slide 5
01
Backend foundation
FastAPI, CORS, config, MongoDB connection, health checks, artifact organization
02
Authentication
JWT login, users, roles, protected APIs, web/mobile auth readiness
03
Core data APIs
Vehicles, parts, maintenance records, alerts, dashboard summaries, seed data
04
PM ML integration
Load EV model artifact, expose prediction API, save results, trigger alerts
Project completion target after Phase 04
50%
Milestone result
React web and Flutter mobile remain intact, while FastAPI becomes the backend backbone for MongoDB + ML integration.

## Slide 6
Phase 01 — Backend foundation
Create the backend skeleton and organize the ML artifacts without running them yet
AI Driven Fleet Optimization
PHASE 01
Phase 01–04 implementation plan | Slide 6
Implementation scope
FastAPI project, environment config, health routes, CORS, MongoDB connection utilities, response helpers.
Artifact handling
Extract ev_pm_artifacts.zip, route_prediction_artifacts.zip, and demand_forecasting_artifacts.zip into backend/ml_artifacts.
No feature integration yet
No authentication, no model loading, no frontend API replacement, no route optimizer in this phase.
Area
Deliverable
Verification
Backend
backend/app/main.py + core modules
/api/health returns success
MongoDB
Motor connection utilities
/api/health/db safe even without URI
Artifacts
3 ML artifact folders
ZIP files extracted and documented
Docs
README + .env.example
Developer can run locally
Expected output
A clean backend base that starts reliably and is ready for Phase 02 authentication.

## Slide 7
Phase 02 — Authentication and role foundation
Turn the backend into a protected platform for admin, fleet, planner, maintenance, and driver users
AI Driven Fleet Optimization
PHASE 02
Phase 01–04 implementation plan | Slide 7
User model
email, password_hash, full_name, role, status, timestamps, last_login
Auth endpoints
POST /auth/register, POST /auth/login, GET /auth/me, POST /auth/logout
Security layer
bcrypt password hashing, JWT token creation, role-based dependency guards
Admin
full system access
Fleet Manager
vehicles, dashboards, alerts
Route Planner
routes, deliveries, demand views
Driver
mobile-only route and alerts
Phase 02 completion criterion
A user can log in through backend JWT and access protected test endpoints; frontend and mobile integration may remain minimal until later phase.

## Slide 8
Phase 03 — Core domain APIs
Implement the data backbone required by the predictive maintenance workflow
AI Driven Fleet Optimization
PHASE 03
Phase 01–04 implementation plan | Slide 8
Vehicles
CRUD, status, mileage, assigned driver, last service date
Vehicle Parts
part list, risk status, service cycle, last maintained date
Maintenance
records, costs, notes, completion status, history timeline
Alerts
risk alerts, overdue alerts, resolved/unresolved states
API group
Key endpoints
Purpose
Vehicles
GET/POST/PUT /api/vehicles
Fleet registry and dashboard source
Parts
GET /api/vehicles/{id}/parts
Component-level health view
Maintenance
POST /api/vehicles/{id}/maintenance
Service history and risk reset
Alerts
GET/PUT /api/alerts
Risk communication workflow
Phase 03 completion criterion
Web app can be gradually switched from mock vehicle/maintenance data to real backend data.

## Slide 9
Phase 04 — Predictive maintenance ML integration
Load the EV artifact and expose real prediction APIs for the web dashboard
AI Driven Fleet Optimization
PHASE 04
Phase 01–04 implementation plan | Slide 9
Input
EV sensor / usage features
Model
ev_predictive_maintenance_model_bundle.joblib
API output
probability, type, RUL estimate
Action
save + alert + dashboard
Endpoint examples
POST /api/predictive-maintenance/predict
GET /api/predictive-maintenance/fleet-risk
POST /api/predictive-maintenance/refresh
Business rule
If failure probability ≥ 70%, generate a critical alert and mark vehicle/part as high risk.
Boundary
Use RUL as estimated window only; current RUL regression is weak and must not be overclaimed.

## Slide 10
Database collections by Phase 04
Only create the collections required to make the maintenance workflow real and persistent
AI Driven Fleet Optimization
MONGODB
Phase 01–04 implementation plan | Slide 10
users
admin, fleet manager, maintenance manager, route planner, driver
vehicles
registration, model, mileage, status, assigned driver
vehicle_parts
part name, risk score, last service, next maintenance estimate
maintenance_records
service date, part, cost, issue, notes, completion state
maintenance_predictions
failure probability, maintenance type, confidence, RUL estimate, model version
alerts
severity, message, related vehicle/part, status, created/resolved timestamps
audit/logs
optional development log for prediction calls and maintenance updates
Design principle
Do not mix forecast, route, and maintenance data in one collection. Keep domain collections clean for later integration.

## Slide 11
Web and mobile integration boundary
By Phase 04, web integration starts; mobile gets backend-ready but route functionality remains later
AI Driven Fleet Optimization
FRONTENDS
Phase 01–04 implementation plan | Slide 11
React web app changes
Replace mock services for vehicles, maintenance history, prediction results, alerts, and dashboard summary with FastAPI calls.
Flutter mobile app changes
Keep mock route UI if needed, but prepare auth and driver API service layer for later connection.
Frontend area
Phase 04 status
Reason
Web dashboard
partially API-backed
maintenance demo must be real
Vehicle detail page
API-backed
shows model predictions and alerts
Mobile driver route
not yet integrated
route optimizer is later phase
Mobile alerts
API-ready only
push/driver alert workflow later
Practical scope control
Phase 04 should not attempt to connect every mobile feature; focus on a stable predictive maintenance backend demo first.

## Slide 12
Risks and controls
Prevent the implementation from becoming unstable before the 50% milestone
AI Driven Fleet Optimization
RISK CONTROL
Phase 01–04 implementation plan | Slide 12
Risk 1: over-scoping
Trying to integrate all three ML models before backend/auth is stable.
Control
Integrate only EV predictive maintenance by Phase 04; organize route/demand artifacts for later.
Evidence
Route and demand artifacts already exist, so they do not block Phase 04.
Risk 2: weak model claims
RUL regression and graph-enhanced demand results are not strong enough yet.
Control
Use failure probability as the main maintenance output; label RUL as estimated only.
Evidence
EV failure model F1 = 84.59%; RUL R² ≈ 0, so claims must be precise.
Risk 3: front-end breakage
Replacing mock services too early can break working screens.
Control
Introduce API service wrappers and migrate one screen at a time.
Evidence
Existing UI is valuable; preserve it and only swap data sources.

## Slide 13
Phase 04 completion checklist
Use this to prove first milestone readiness to the supervisor
AI Driven Fleet Optimization
CHECKLIST
Phase 01–04 implementation plan | Slide 13
✓
Backend runs
FastAPI starts and /api/health works
✓
MongoDB connected
DB health endpoint returns configured/connected status
✓
Auth works
JWT login and protected route test pass
✓
Core APIs ready
vehicles, parts, maintenance, alerts CRUD complete
✓
EV model loaded
prediction endpoint returns risk output
✓
Results persisted
predictions and alerts saved to MongoDB
✓
Web screen connected
vehicle/prediction dashboard uses real API
✓
Demo seed data
admin user, vehicles, maintenance records exist
Milestone statement
At Phase 04, the project demonstrates a real predictive maintenance pipeline from web input to backend ML inference to stored alert.